## Slide 1: Thesis Meeting
09/05/2022

## Slide 2: What I did last week
Fully test the system
Shared annotation system with first users for feedback
Explored the system
Working on algorithm for in-expansion

## Slide 3: Questions? 1/2
WikiDump is different then Wikipedia
How are we annotating multilingual acronyms? Do we take the language of the acronym or the expansion ?
How are we handling acronyms like:
  Националната хокейна лига на САЩ и Канада (NHL) – considered as out expansion
  National Research Foundation of Korea (NRF) = National Research Foundation
  ПК Екогласност – ПК is part of the name of a political party, however, do we take the whole thing, or just ПК, just political party
Unit measures in Bulgarian are sometimes used with ‘.’ at the end, do we have to annotate both ‘’m.” and “m” separately or it is enough to annotate one of them? Same for т.нар. , пр.н.е., etc – add both

## Slide 4: Questions? 2/2
Is “the persistence of mortar cues” the same as “persistence of mortar cues” when PMC is the acronym?

## Slide 5: This week
Share annotation system with more people
Continue working on the algorithm for in expansion
  Start working on multi language algorithm - out
Focus on writing the methodology
Get started processing the annotations
Check text extractor
Update system to have the None of the above - done

## Slide 6: Timeline
Deadline | Actions
16th May | Extension of In expansion algorithm
22nd May | Annotation finalization
25th May | Creation of Dataset from annotated data
1st June | Test the system with the created data set, feedback from the results & Methodology section finalized
8th June | Evaluate results, plus improvements to algorithm
15th June | Results section and Discussion
22nd June | Conclusion and Abstract finalized
29th June | Finalizing thesis