## Slide 1: Thesis Meeting
16/05/2022

## Slide 2: What I did last week
Share annotation system with more people - Done, current status 73/242 annotations are done (121 docs)
Continue working on the algorithm for in expansion - In progress
Focus on writing the methodology - In progress
Get started processing the annotations - In progress
Check the text extractor - done, seems like we are not stripping anything
Update system to have the None of the above - Done

## Slide 3: Questions? 1/2

## Slide 4: This week
Continue working on the algorithm for the expansion
Continue on writing the methodology
Prepare the Analysis and Results report
Finish the script for processing the annotations work - together with the rest
Get more annotators

## Slide 5: Timeline
Deadline | Actions
22nd May | Extension of In expansion algorithm
22nd May | Annotation finalization
25th May | Creation of Dataset from annotated data
1st June | Test the system with the created data set, feedback from the results & Methodology section finalized
8th June | Evaluate results, plus improvements to algorithm
15th June | Results section and Discussion
22nd June | Conclusion and Abstract finalized
29th June | Finalizing thesis